## Burndown_chart_all_days
User Story ID | Release Backlog | Estimated Story Points | Sprint #1 Day 1 - 29/11 | Day 2 - 30/11 | Day 3 - 01/12 | Sprint #2 Day 4 - 02/12 | Day 5 - 04/12 | Day 6 - 05/12 | Sprint #3 Day 7 - 06/12 | Day 8 - 07/12 | Day 9 - 08/12 | Sprint #4 Day 10 - 09/12 | Day 11 - 10/12 | Day 12 - 11/12 | Sprint #5 Day 13 - 12/12 | Day 14 - 13/12 | Day 15 - 14/12 | Total Story Points
1 | As a user logged in as an admin, I want to be able to manage products. | 100 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100
2 | As a user logged in as an admin, I want to have access to an invoice history. | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55
3 | As a user logged in as an admin, I want to be able to check the orders. | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40
4 | As a user logged in as an admin, I want to be able to manage pickers. | 60 | 60 | 60 | 60 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60
5 | As a user logged in as an admin, I want to be able to register merchandise received by the warehouse. | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 0 | 0 | 0 | 0 | 55
6 | As a user logged in as an admin, I want to be able to manage the suppliers. | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 40
7 | As a user logged in as an admin, I want to be able to manage the customers. | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 40
8 | As a user logged in as an admin, I want to be able to manage the stocks in storage. | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 40
9 | As a user logged in as a picker, I want to be able to start and end my shift. | 25 | 25 | 25 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
10 | As a user logged in as a picker, I want to be able to start an order. | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 60
11 | As a user logged in as a picker, I should be able to stop at any point during the order and call it incomplete, and I should be able to finish an order | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 90
12 | As a user logged in as a customer, I would like to see a list of different categories and pick the products I want from each category. | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40
13 | As a user logged in as a customer, I want to be able to specify a certain amount for each product I am ordering and provide the date of shipment. | 30 | 30 | 30 | 30 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30
14 | As a user, we want to be able to login to the system based on the different people who are going to use the system. | 20 | 20 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
15 | As developers, we are going to create a use case diagram along with use case descriptions for our system. | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 8
16 | As developers, we are going to create activity diagrams for each use case description. | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 8
17 | As developers, we are going to create one sequence diagram based on one use case description in which we find is most interesting. | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 3
18 | As developers, we are going to document each step we do. We will have documentation for each design pattern we implement. | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8
19 | As developers, we are going to document the client/server system. | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 5
20 | As developers, we are going to document SCRUM. | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 10
21 | As developers, we are going to have documentation for Unified Processes. | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3
22 | As developers, we are going to create a project report. | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 50
23 | As developers, we are going to create a process report. | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 0 | 25
| Work Days | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| Ideal Remaining Effort | 815 | 760.6667 | 706.3333 | 652 | 597.6667 | 543.3333 | 489 | 434.6667 | 380.3333 | 326 | 271.6667 | 217.3333 | 163 | 108.6667 | 54.3333 | -1.279e-13 | 815
| Actual Remaining Effort | 815 | 815 | 815 | 715 | 715 | 670 | 500 | 500 | 500 | 445 | 295 | 255 | 101 | 101 | 98 | 0 | 815

## sprint#1
User Story Id | Task Number | Tasks | Estimate Story Points | Day 1 - 29/11 | Day 2 - 30/11 | Day 3 - 01/12 | Total work done | Responsible
1 | 1 | Create an EER diagram and a conceptual model for Product table, Category table, Pallet table, Supplier table, ProductSuppliers table, and CityPostalCode table. | 2 | 2 | 0 | 0 | 2 | All
1 | 2 | Implement a Product class. | 2 | 2 | 0 | 0 | 2 | Bianca
1 | 3 | Implement a Category class. | 2 | 2 | 0 | 0 | 2 | Bianca
1 | 4 | Implement a Pallet class. | 2 | 2 | 0 | 0 | 2 | Bianca
1 | 5 | Implement a Supplier class. | 2 | 0 | 2 | 0 | 2 | Tamara
1 | 6 | Implement a ProductSuppliers class. | 2 | 0 | 2 | 0 | 2 | Tamara
1 | 7 | Implement a CityPostalCode class. | 2 | 0 | 2 | 0 | 2 | Tamara
1 | 8 | Create a Product table. | 2 | 2 | 0 | 0 | 2 | Bashar
1 | 9 | Create a Category table. | 2 | 2 | 0 | 0 | 2 | Bashar
1 | 10 | Create a Pallet table. | 2 | 2 | 0 | 0 | 2 | Bashar
1 | 11 | Create a Supplier table. | 2 | 0 | 2 | 0 | 2 | Bashar
1 | 12 | Create a ProductSuppliers table | 2 | 0 | 2 | 0 | 2 | Bashar
1 | 13 | Create a CityPostalCode table. | 2 | 0 | 2 | 0 | 2 | Bashar
1 | 14 | Create a client/server with RMI and Remote Observer. | 3 | 2 | 0 | 1 | 3 | Tamara/Bashar
1 | 15 | Implement the functionality to add a new product to the database. | 3 | 3 | 0 | 0 | 3 | Cristi
1 | 16 | Implement the functionality to delete an existing product from the database. | 2 | 2 | 0 | 0 | 2 | Cristi
1 | 17 | Implement the functionality to add a new category to the database. | 2 | 2 | 0 | 0 | 2 | Cristi
1 | 18 | Implement the functionality to delete an existing category from the database. | 1 | 1 | 0 | 0 | 1 | Cristi
1 | 19 | Implement the functionality that retrieves all the products' information based on the product ID. | 3 | 3 | 0 | 0 | 3 | Cristi/Bashar
1 | 20 | Implement the functionality that allows the user to enter a certain date and retrieves all the products that will expire before that date. | 7 | 7 | 0 | 0 | 7 | Cristi/Bashar
| 21 | Implement the functionality that retrieves all the products for a category. | 2 | 0 | 0 | 2 | 2 | Bashar/Cristi
1 | 22 | Create a GUI for the server side. | 3 | 3 | 0 | 0 | 3 | Tamara
1 | 23 | Create a GUI page for adding a new product and category. | 5 | 1 | 4 | 0 | 5 | Bianca
1 | 24 | Create a GUI page for deleting an existing product. | 5 | 0 | 5 | 0 | 5 | Cristi
1 | 25 | Create a GUI page for deleting an existing category. | 5 | 2 | 3 | 0 | 5 | Bashar
1 | 26 | Create a GUI page that allows the user to search for a certain product using the product ID and lists the information about the product (even the ones on different pallets). | 5 | 2 | 3 | 0 | 5 | Tamara
1 | 27 | Create a GUI page that allows the user to retrieve the products that have expiration dates before the date inputted by the user. | 5 | 3 | 2 | 0 | 5 | Bianca
1 | 28 | Create a GUI page to print out all the products in the system based on the category chosen. | 3 | 0 | 0 | 3 | 3 | Bashar
1 | 29 | Combine all GUI with functionality. | 20 | 0 | 5 | 15 | 20 | Cristi/Bashar
15 | 30 | Create a use case diagram, and use case descrptions for all the functionalities. | 2 | 0 | 0 | 2 | 2 | Bianca/Tamara
16 | 31 | Create activity diagrams for each use case created. | 2 | 0 | 0 | 2 | 2 | Bianca/Tamara
20 | 32 | Document SCRUM. | 2 | 0.5 | 0.5 | 1 | 2 | Tamara
23 | 33 | Document supervisor meeting. | 5 | 0 | 5 | 0 | 5 | Bianca
|  | Work Days | 0 | 1 | 2 | 3
|  | Ideal Remaining Effort | 111 | 74 | 37 | 0
|  | Actual Remaining Effort | 111 | 65.5 | 26 | 0

## sprint#2
User Story Id | Task Number | Tasks | Estimate Story Points | Day 1 - 02/12 | Day 2 - 03/12 | Day 3 - 05/12 | Total work done | Responsibility
4 | 1 | Add Pickers and PickersSchedule table to EER diagram. | 2 | 2 | 0 | 0 | 2 | All
4 | 2 | Implement a Picker class. | 1 | 1 | 0 | 0 | 1 | Bianca
4 | 3 | Implement a PickersSchedule class. | 1 | 1 | 0 | 0 | 1 | Bianca
4 | 4 | Create a Picker table. | 1 | 1 | 0 | 0 | 1 | Tamara
4 | 5 | Create a PickersSchedule table. | 1 | 1 | 0 | 0 | 1 | Tamara
4 | 6 | Create a GUI page to add a picker. | 5 | 5 | 0 | 0 | 5 | Tamara
4 | 7 | Create a GUI page to remove a picker. | 5 | 0 | 5 | 0 | 5 | Cristi
4 | 8 | Create a GUI page to display two lists of pickers (one list with registered pickers at the warehouse, and one list of pickers currently at work). | 10 | 0 | 5 | 5 | 10 | Bianca
4 | 9 | Implement the functionality to add a picker to the system. | 3 | 0 | 0 | 3 | 3 | Cristi
4 | 10 | Implement the functionality to display the two lists of pickers. | 15 | 0 | 0 | 15 | 15 | Crist/Bashar
4 | 11 | Implement the functionality to remove a picker. | 3 | 0 | 0 | 3 | 3 | Cristi
4 | 12 | Combine the GUI pages with the funtionalities. | 6 | 0 | 0 | 6 | 6 | Cristi
14 | 13 | Create a GUI page to allow the user to log in. | 5 | 0 | 5 | 0 | 5 | Bashar
14 | 14 | Implement the functionality to log in as different users. | 10 | 0 | 8 | 2 | 10 | Bashar
14 | 15 | Combine the GUI page with the funtionality. | 5 | 0 | 5 | 0 | 5 | Bashar
9 | 16 | Create a GUI page to have the picker check in and check out. | 5 | 0 | 5 | 0 | 5 | Bianca
9 | 17 | Implement the functionality to register when the picker has checked in/checked out. | 20 | 0 | 20 | 0 | 20 | Bashar
12 | 18 | Add Order, Item, and Customer tables to EER diagram. | 2 | 0 | 0 | 2 | 2 | Bashar
12 | 19 | Implement an Order class. | 2 | 0 | 0 | 2 | 2 | Bianca
12 | 20 | Implement a an Item class. | 2 | 0 | 0 | 2 | 2 | Bianca
12 | 21 | Implement a Customer class. | 2 | 0 | 0 | 2 | 2 | Bianca
12 | 22 | Create an Order table. | 2 | 0 | 0 | 2 | 2 | Tamara
12 | 23 | Create an Item table. | 2 | 0 | 0 | 2 | 2 | Tamara
12 | 24 | Create a Customer table. | 2 | 0 | 0 | 2 | 2 | Tamara
12 | 25 | Create a GUI page to make an order. | 30 | 10 | 10 | 10 | 30 | All
12+13 | 26 | Implement the functionality to make an order and add to the order table. | 20 | 0 | 0 | 20 | 20 | Bashar/Tamara
3 | 27 | Create a GUI page to show a list of available orders. | 5 | 5 | 0 | 0 | 5 | Bianca/Cristi
3 | 28 | Create a GUI page to show a list of in progress orders. | 5 | 5 | 0 | 0 | 5 | Bianca/Cristi
3 | 29 | Implement the functionality to show the lists. | 15 | 0 | 0 | 15 | 15 | Cristi
3 | 30 | Combine the GUI pages with the funtionalities. | 9 | 0 | 3 | 6 | 9 | All
15 | 31 | Create use case descriptions for all the functionalities. | 2 | 0 | 2 | 0 | 2 | Bianca/Tamara
16 | 32 | Create activity diagrams for all the use case descriptions. | 2 | 0 | 2 | 0 | 2 | Bianca/Tamara
20 | 33 | Document SCRUM | 2 | 0.5 | 0.5 | 1 | 2 | Tamara
|  | Work Days | 0 | 1 | 2 | 3
|  | Ideal Remaining Effort | 187 | 124.6667 | 62.3333 | 0
|  | Actual Remaining Effort | 187 | 156 | 93 | 0
Add InProgressOrders table to EER diagram.
Implement an InProgressOrder class.
Create an InProgressOrder table.
Create a GUI page to show a list of available orders.
Create a GUI page to show a list of in progress orders.
Implement the functionality to show the lists.
Create a use case description for checking orders.
Create an activity diagram for the use case description.

## sprint#3
User Story Id | Task Number | Tasks | Estimate Story Points | Day 1 - 06/12 | Day 2 - 07/12 | Day 3 - 08/12 | Total work done | Responsibility
10 | 1 | Create a GUI page to start an order. | 15 | 10 | 3 | 2 | 15 | All
10 | 2 | Implement the functionality to start an order. | 15 | 0 | 10 | 5 | 15 | Bashar/Tamara
10 | 3 | Combine the GUI pages with the funtionalities. | 30 | 0 | 10 | 14 | 24 | Bashar
11 | 4 | Create a GUI page to finish an order or mark it as incomplete. | 20 | 0 | 0 | 15 | 15 | Bashar
11 | 5 | Implement the functionality to finish an order. | 22 | 0 | 0 | 15 | 15 | Bashar/Tamara
11 | 6 | Implement the functionality to mark an order as incomplete. | 30 | 0 | 0 | 15 | 15 | Bashar
11 | 7 | Combine the GUI pages with the funtionalities. | 18 | 0 | 0 | 10 | 10 | Bashar
2 | 8 | Add Invoice table to EER diagram. | 2 | 2 | 0 | 0 | 2 | Cristi
2 | 9 | Implement an Invoice class. | 2 | 2 | 0 | 0 | 2 | Cristi
2 | 10 | Create an Invoice table. | 2 | 2 | 0 | 0 | 2 | Cristi
2 | 11 | Create a GUI page to show a list of invoices. | 15 | 7 | 8 | 0 | 15 | Cristi
2 | 12 | Implement the functionality to show the list of invoices. | 8 | 2 | 2 | 4 | 8 | Cristi
2 | 13 | Combine the GUI pages with the funtionalities. | 20 | 0 | 15 | 5 | 20 | Cristi
15 | 14 | Create use case descriptions for all the functionalities. | 2 | 0 | 0 | 2 | 2 | Bianca/Tamara
16 | 15 | Create activity diagrams for all the use case descriptions. | 2 | 0 | 0 | 2 | 2 | Bianca/Tamara
20 | 16 | Document SCRUM. | 2 | 0.5 | 0.5 | 1 | 2 | Tamara
23 | 17 | Document interview with Reitan. | 5 | 5 | 0 | 0 | 5 | Bianca
|  | Work Days | 0 | 1 | 2 | 3
|  | Ideal Remaining Effort | 203 | 135.3333 | 67.6667 | 0
|  | Actual Remaining Effort | 203 | 178 | 130 | 41

## sprint#4
User Story Id | Task Number | Tasks | Estimate Story Points | Day 1 - 09/12 | Day 2 - 10/12 | Day 3 - 11/12 | Total work done | Responsibility
11 | 1 | Create a GUI page to finish an order or mark it as incomplete. | 15 | 15 | 0 | 0 | 15 | Bashar
11 | 2 | Implement the functionality to finish an order. | 15 | 15 | 0 | 0 | 15 | Bashar/Tamara
11 | 3 | Implement the functionality to mark an order as incomplete. | 15 | 15 | 0 | 0 | 15 | Bashar/Tamara
11 | 4 | Combine the GUI pages with the funtionalities. | 10 | 10 | 0 | 0 | 10 | Bashar/Tamara
6 | 5 | Create a GUI page to add a supplier. | 5 | 5 | 0 | 0 | 5 | Cristi
6 | 6 | Implement the functionality to add a supplier | 8 | 8 | 0 | 0 | 8 | Cristi
6 | 7 | Combine the GUI page with the functionality. | 7 | 7 | 0 | 0 | 7 | Cristi
6 | 8 | Create a GUI page to print a list of all suppliers. | 5 | 5 | 0 | 0 | 5 | Cristi
6 | 9 | Implement the functionality to show the list of suppliers. | 8 | 8 | 0 | 0 | 8 | Cristi
6 | 10 | Combine the GUI page with the functionality. | 7 | 7 | 0 | 0 | 7 | Cristi
7 | 11 | Create a GUI page to add a customer. | 5 | 5 | 0 | 0 | 5 | Bianca
7 | 12 | Implement the functionality to add a customer. | 8 | 0 | 0 | 8 | 8 | Cristi
7 | 13 | Combine the GUI page with the functionality. | 7 | 0 | 0 | 7 | 7 | Cristi
7 | 14 | Create a GUI page to print a list of all customers. | 5 | 0 | 0 | 5 | 5 | Cristi
7 | 15 | Implement the functionality to show the list of customers. | 8 | 0 | 0 | 8 | 8 | Cristi
7 | 16 | Combine the GUI page with the functionality. | 7 | 0 | 0 | 7 | 7 | Cristi
5 | 17 | Create a GUI page to register the goods. | 10 | 10 | 0 | 0 | 10 | Cristi
5 | 18 | Implement the functionality to register the incoming goods. | 30 | 0 | 15 | 15 | 30 | Cristi
5 | 19 | Combine the GUI page with the functionality. | 15 | 0 | 0 | 15 | 15 | Cristi
8 | 20 | Create a GUI page to view the stocks under a certain amount. | 5 | 0 | 0 | 5 | 5 | Cristi
8 | 21 | Implement the functionality to view the stocks under a certain amount. | 20 | 0 | 0 | 20 | 20 | Cristi
8 | 22 | Combine the GUI page with the functionality. | 15 | 0 | 0 | 15 | 15 | Cristi
15 | 23 | Create use case descriptions for all the functionalities. | 2 | 0 | 0 | 2 | 2 | Bianca/Tamara
16 | 24 | Create activity diagrams for all the use case descriptions. | 2 | 0 | 0 | 2 | 2 | Bianca/Tamara
17 | 25 | Create a sequence diagram for one of the use case descriptions. | 3 | 0 | 0 | 3 | 3 | Bianca/Tamara
22 | 26 | Write the abstract for the project. | 5 | 0 | 5 | 0 | 5 | Bianca/Tamara
20 | 27 | Document SCRUM. | 2 | 0.5 | 0.5 | 1 | 2 | Tamara
|  | Work Days | 0 | 1 | 2 | 3
|  | Ideal Remaining Effort | 244 | 162.6667 | 81.3333 | 0
|  | Actual Remaining Effort | 244 | 133.5 | 113 | 0

## sprint#5
User Story Id | Task Number | Tasks | Estimate Story Points | Day 1 - 09/12 | Day 2 - 10/12 | Day 3 - 11/12 | Total work done | Responsibility
18 | 1 | Document the MVC for our system. | 2 | 0 | 2 | 0 | 2 | Bashar
18 | 2 | Document the Singleton pattern. | 2 | 0 | 2 | 0 | 2 | Bashar
18 | 3 | Document the Remote Observer pattern. | 2 | 0 | 0 | 2 | 2 | Bashar
18 | 4 | Document the Adapter pattern. | 2 | 0 | 0 | 2 | 2 | Bashar
19 | 5 | Document the client/server system using RMI. | 5 | 0 | 0 | 5 | 5 | Bashar
22 | 6 | Create a full class diagram. | 3 | 0 | 0 | 3 | 3 | All
22 | 7 | Create a logical mapping for the EER diagram. | 2 | 0 | 0 | 2 | 2 | Cristian
22 | 8 | Create a worksheet to be run after running the database to populate it. | 2 | 0 | 0 | 2 | 2 | Bashar
21 | 9 | Document UP. | 3 | 1 | 2 | 0 | 3 | Bianca
22 | 10 | Write Introduction for Project Report. | 3 | 3 | 0 | 0 | 3 | Tamara
22 | 11 | Write nonfunctional requirements. | 5 | 5 | 0 | 0 | 5 | Tamara
22 | 12 | Write actor descriptions for each actor of the system. | 2 | 0 | 2 | 0 | 2 | Tamara
22 | 13 | Document the GUI design. | 10 | 0 | 0 | 10 | 10 | Bianca
22 | 14 | Document the testing of the system using the product backlog. | 5 | 5 | 0 | 0 | 5 | Tamara
22 | 15 | Document the results of the system. | 3 | 0 | 3 | 0 | 3 | Bianca
22 | 16 | Write the discussion section of the project report. | 2 | 0 | 2 | 0 | 2 | Bianca
22 | 17 | Write a conclusion for the system. | 3 | 0 | 3 | 0 | 3 | Bianca
22 | 18 | Create a User Guide for the system. | 5 | 0 | 2 | 3 | 5 | Cristian
20 | 19 | Document SCRUM. | 2 | 0.5 | 0.5 | 1 | 2 | Tamara
23 | 20 | Document the reflection on project work for each group member. | 10 | 0 | 2 | 8 | 10 | All
23 | 21 | Add to the Bloom analysis based on knowledge after the project. | 5 | 0 | 5 | 0 | 5 | All
|  | Work Days | 0 | 1 | 2 | 3
|  | Ideal Remaining Effort | 78 | 52 | 26 | 0
|  | Actual Remaining Effort | 78 | 63.5 | 38 | 0